## RACI
Traditional | [5 empty] | Scrum
Customer | Product Manager | Project Manager | Developers | Line Manager | Distribution of the Reponsiblities in a Scrum Project | Line Manager | Dev-Team | Product Owner | Scrum Master | Customer
|  | R |  | I | Select Team Members | R |  | A
|  |  |  | R | Select Tools |  | R
|  | R |  |  | Plan Tasks |  | R
|  | R |  |  | Ensure good implementations |  | R
|  |  |  | R | Define and Impose Standards | C | R
|  | R |  |  | Coordinate Work |  | R
A | A | R |  |  | Budget |  |  | R |  | A
| A | R |  |  | Scope (release) |  |  | R |  | A
|  | R |  |  | Scope (sprint) |  | RA | R
|  | R | C |  | Estimates |  | R
|  | R |  |  | Priorities |  |  | R
| A | R | CI |  | Commit to Delivery Dates (release) |  |  | R
|  | R |  |  | Assign Tasks |  | R
| R |  |  |  | Instructions from Customer |  |  | R
|  | R |  |  | Other Communication with Customer |  |  | R
|  | A(?) |  |  | Remove Impediments |  |  |  | R
|  | R |  |  | Reporting to Management |  | C | R
|  | R |  |  | Change Management |  |  | R
|  | R |  |  | Risk Management |  | C | R
|  | R |  | C | Compliance |  | C | R
R | R |  |  |  | Return on Investment |  |  | R
|  |  |  | R | Improving Invididual Performance |  |  |  | R
|  |  |  | - | Improving Team Performance |  |  |  | R
|  |  |  | n/a | Not Asked
|  |  |  | Blank, * | Marginally involved
|  |  |  | ** | Involved
|  |  |  | *** | Shared Responsilbity
|  |  |  | **** | Primary Responsibility
Classic Results based on a poll of Participants during a Scrum CSM/Jumpstart course, August 27, 2010
v 1.1 © 2010 Peter Stevens
Last Revision: Aug 29, 2010
Includes Material from M&T Poppendieck

## Dev Team
| Distribution of the Reponsiblities of the Development Team | Traditional | Scrum
| Select Team Members |  | ***
| Select Tools | ** | ****
| Plan Tasks |  | ****
| Ensure good implementations | ** | ****
| Define and Impose Standards |  | ****
| Coordinate Work |  | ****
Budget
Scope (release)
| Scope (sprint) |  | ****
| Estimates |  | ****
| Priorities |  | **
| Commit to Delivery Dates (release) | *
| Assign Tasks |  | **
Instructions from Customer
| Other Communication with Customer |  | ***
Remove Impediments
Reporting to Management
| Change Management |  | ***
| Risk Management |  | ***
| Compliance |  | ***
Return on Investment
| Improving Performance |  | ***
n/a | Not Asked
Blank, * | Marginally involved
** | Involved
*** | Shared Responsilbity
**** | Primary Responsibility
Traditional Results based on a poll of Participants during a Scrum CSM/Jumpstart course, August 27, 2010
v 1.0 © 2010 Peter Stevens
Last Revision: Aug 29, 2010

## PO vs. PL
| Distribution of the Reponsiblities of the Project Leader | Project Manager | Product Owner | ScrumMaster
| Select Team Members | *** | *** | **
| Select Tools | **** |  |  | 1
| Plan Tasks | **** |  |  | 1
| Ensure good implementations | **** | ** |  | 1
| Define and Impose Standards | *** | ** | **
| Coordinate Work | **** |  |  | 1
| Budget | *** | **** |  |  | 1
| Scope (release) | *** | **** |  |  | 1
| Scope (sprint) | n/a | **
| Estimates | ***
| Priorities | **** | **** |  | 1 | 1
| Commit to Delivery Dates (release) | **** | **** |  | 1 | 1
| Assign Tasks | **** | **** |  | 1 | 1
| Instructions from Customer | *** | **** |  |  | 1
| Other Communication with Customer | *** | ***
| Remove Impediments | **** |  | **** | 1
| Reporting to Management | **** | **** | ** | 1 | 1
| Change Management | **** | *** |  | 1
| Risk Management | **** | *** | *** | 1
| Compliance | **** | *** | *** | 1
| Return on Investment |  | **** |  |  | 1
| Improving Performance | ? | *** | ****
[5 empty] | 0 | 12
n/a | not applicable
Blank, * | Marginally involved
** | Involved
*** | Shared Responsilbity
**** | Primary Responsibility
Classic Results based on a poll of Participants during a Scrum CSM/Jumpstart course, August 27, 2010
v 1.0 © 2010 Peter Stevens
Last Revision: Aug 29, 2010