## RACI
| Traditional | [5 empty] | Scrum
| Customer | Product Manager | Project Manager | Developers | Line Manager | Distribution of the Reponsiblities in a Scrum Project | Line Manager | Dev-Team | Product Owner | Scrum Master | Customer
Project Manager |  |  | R |  | I | Select Team Members | R |  | A | C
[5 empty] | R | Select Tools |  | R |  | C
|  |  | R |  |  | Plan Tasks |  | R
|  |  | R |  |  | Ensure good implementations |  | R |  | C
[5 empty] | R | Define and Impose Standards | C | R
|  |  | R |  |  | Coordinate Work |  | R
| A | A | R |  |  | Budget |  |  | R |  | A
|  | A | R |  |  | Scope (release) |  |  | R |  | A
|  |  | R |  |  | Scope (sprint) |  | RA | R
|  |  | R | C |  | Estimates |  | R
|  |  | R |  |  | Priorities |  |  | R
|  | A | R | CI |  | Commit to Delivery Dates (release) |  |  | R
|  |  | R |  |  | Assign Tasks |  | R
|  | R |  |  |  | Instructions from Customer |  |  | R
|  |  | R |  |  | Other Communication with Customer |  |  | R
|  |  | A |  |  | Remove Impediments |  |  |  | R
|  |  | R |  |  | Reporting to Management |  | C | R
|  |  | R |  |  | Change Management |  |  | R
|  |  | R |  |  | Risk Management |  | C | R
|  |  | R |  | C | Compliance |  | C | R
| R | R |  |  |  | Return on Investment |  |  | R
[5 empty] | R | Improving Invididual Performance |  |  |  | R
[5 empty] | - | Improving Team Performance |  |  |  | R
Product Manager* | [5 empty] | Responsible for business success
Understands the customers’ job
Understands the technology
Created the initial product vision
Assembled the business team
Connects the team with customers
Clarifies the business constraints
Expects the team to make decisions
Arbitrates trade-offs if necessary
Pays attention to the details
Defends the product vision
Inspires passion
Technical Lead* | [5 empty] | Master in a critical technical area
Recruits and develops people
Connects people with teams
Acts as a teacher and mentor
Deeply knowledgeable & involved
Reviews and guides work
Ensures technical excellence
Sets technical standards
Clarifies the technical constraints
Plans for future technical needs
Defends the technical vision
Inspires Passion
[5 empty] | R | Responsible
[5 empty] | A | Accountable
[5 empty] | C | Consulted
[5 empty] | I | Informed
v 1.1 © 2010 Peter Stevens
Last Revision: Aug 29, 2010
*Job Descriptions © M&T Poppendieck, used by permission

## RACI-Blank
| Traditional | [5 empty] | Scrum
| Customer | Product Manager | Project Manager | Developers | Line Manager | Distribution of the Reponsiblities in a Scrum Project | Line Manager | Dev-Team | Product Owner | Scrum Master | Customer
Project Manager | [5 empty] | Select Team Members
Select Tools
Plan Tasks
Ensure good implementations
Define and Impose Standards
Coordinate Work
Budget
Scope (release)
Scope (sprint)
Estimates
Priorities
Commit to Delivery Dates (release)
Assign Tasks
Instructions from Customer
Other Communication with Customer
Remove Impediments
Reporting to Management
Change Management
Risk Management
Compliance
Return on Investment
Improving Invididual Performance
Improving Team Performance
Product Manager* | [5 empty] | Responsible for business success
Understands the customers’ job
Understands the technology
Created the initial product vision
Assembled the business team
Connects the team with customers
Clarifies the business constraints
Expects the team to make decisions
Arbitrates trade-offs if necessary
Pays attention to the details
Defends the product vision
Inspires passion
Technical Lead* | [5 empty] | Master in a critical technical area
Recruits and develops people
Connects people with teams
Acts as a teacher and mentor
Deeply knowledgeable & involved
Reviews and guides work
Ensures technical excellence
Sets technical standards
Clarifies the technical constraints
Plans for future technical needs
Defends the technical vision
Inspires Passion
[5 empty] | R | Responsible | Last Revision: Aug 29, 2010
[5 empty] | A | Accountable
[5 empty] | C | Consulted
[5 empty] | I | Informed
v 1.1 © 2010 Peter Stevens
*Job Descriptions © M&T Poppendieck, used by permission